Galway County Council

Recommendation of the European Parliament and the Council Providing for the Minimum Criteria for Environmental Inspections in Member States (2001/331/EC)

Inspection & Compliance plan under RMCEI 2026

Note from the Director:

The RMCEI Plan for 2026 sets out Galway County Council’s commitment to delivering a robust, risk‑based and intelligence‑led programme of environmental inspection and enforcement across the county. As the environmental challenges facing our communities continue to evolve, this plan provides a clear framework for how we will prioritise our resources, strengthen compliance, and protect the natural environment that underpins the social and economic wellbeing of Galway. Through the implementation of this RMCEI Plan, Galway County Council aims to deliver high‑quality regulatory oversight, safeguard public health, and protect the county’s unique natural heritage. By combining strong governance, professional expertise, and a commitment to continuous improvement, we will ensure that our environmental enforcement programme continues to meet the highest standards and supports a cleaner, healthier and more sustainable Galway.

Acknowledgments:

I wish to acknowledge the hard work and dedication of Ann Dolan, Senior Executive Scientist and the team in the Environment unit for the development of the RMCEI plan for Galway County for 2026.

Approved by Directors of Services

Eileen Ruane

Name: Eileen Ruane

Position: Director of Services,

Human Resources, City and County Libraries & Environment

Date of Approval:

Table of Contents

1.	Introduction	1

1.1	Plan Details	1

1.2	Expected Known Once-Off Challenges that may be Faced in Implementation of this Plan	1

1.3	Staff Structure	1

2.	Priorities for Environmental Enforcement for the Year Ahead	3

2.1	National Environmental Enforcement Priorities for the Year Ahead	3

2.2	Ongoing RMCEI/Local Priorities	4

3.	Risk Assessment	4

4.	Resource Assessment for the Year Ahead	6

4.1	Review of the Achievement of the Previous Years Inspection Targets	6

4.2	Number of Staff Days Available	7

4.3	Environmental Enforcement Training Requirements	8

4.4	Health and Safety	9

5.	Planned Inspections/Other Activities for the Year Ahead	10

5.1	Planned Routine & Non-Routine Inspections	10

5.2	Outstanding Enforcement Actions & Complaints Requiring Resources for the Year Ahead	11

5.3	Summary of Resource Requirements	11

6.	Plan Review Mechanisms	13

7.	Use of Relevant Inspection Templates	13

Appendix 1: Planned Routine & Non-Routine Inspections for the Year Ahead	14

Figures

Figure 1 Council Organogram	2

Tables

Table 1: Plan Details	1

Table 2 Expected Known Once-Off Challenges that may be Faced in Implementation of this Plan (if any) & how these will be Addressed	1

Table 3 National Environmental Priorities Checklist	3

Table 4  Additional Local Priorities	4

Table 5  Work Planned with Regional Lead Authorities	4

Table 6 Selection of Sites for Assessment in the Year Ahead	5

Table 7 Review of Previous Years Inspections	6

Table 8 Resources Available to undertake required Work for the Year Ahead	7

Table 9 Outstanding Enforcement Actions & Complaints to be Closed Out	11

Table 10 Summary of Inspections to Complete and Resources Required for the Year Ahead	11

Table 11 Summary checklist of plan review mechanism	13

Table 12 Summary of waste inspection template use for the reporting year	13

Glossary/Definitions

Activity - The aim of the activity should be to achieve the intermediate outcomes and/or the final environmental outcome associated with the National Priority

Additional Intermediate outcome – Other outcomes, identified by a Council, outside those that have been specified by the EPA in the RMCEI Return template

ATF – Authorised Treatment Facility (processing of ELVs);

Baseline - To measure the progress in achieving the intermediate outcome over time, a baseline value must be established. Data gathered in subsequent years can then be compared to the baseline value in order to measure progress towards achieving the intermediate outcome.

C&D – Construction & Demolition (Waste);

CCMA – County & City Management Association;

CoR – Certificate of Registration;

DAFM – Department of Agriculture Food & Marine;

DCEE – Department of Climate, Energy and the Environment;

DHLGH – Department of Housing, Local Government and Heritage;

DRS – Deposit Return Scheme;

DWWTS – Domestic Wastewater Treatment System;

Environmental inspection according to RMCEI includes:

- site visits,

- monitoring achievement of environmental quality standards,

- consideration of environmental audit reports and statements,

- consideration and verification of any self-monitoring carried out by or on behalf of operators of controlled installations,

- assessing the activities and operations carried out at the controlled installation,

- checking the premises and the relevant equipment (including the adequacy with which it is maintained) and the adequacy of the environmental management at the site,

- checking the relevant records kept by the operators of controlled installations.

ELV – End of Life Vehicle;

EPA – Environmental Protection Agency;

Final Environmental Outcome - is a measurable change in the environment, e.g. cleaner air or improved water quality

GAP – Good Agricultural Practice for the protection of waters Regulations;

LAWPRO – Local Authority Waters Programme;

Metric – A metric is a way of measuring the progress to achieving the intermediate outcome or the objective

NAIP – National Agricultural Inspection Programme

NIECE – Network for Ireland’s Environmental Compliance & Enforcement;

NIP – National Inspection Plan;

Non-routine inspection – an inspection carried out in such cases in response to complaints, in connection with the issuing, renewal or modification of an authorisation, permit or licence, or in the investigation of accidents, incidents and occurrences of non-compliance.

OEE – Office of Environmental Enforcement, EPA;

PMDS – Performance Management and Development System;

PRI/EPRI – Producer Responsibility Initiative or Extended Producer Responsibility Initiative;

RBMP – River Basin Management Plan;

RMCEI – EU Recommendation on Minimum Criteria for Environmental Inspections;

Routine inspection – an inspection carried out as part of a planned inspections programme, e.g. scheduled inspection of a permitted facility, scheduled monitoring of a licensed discharged; compliance assessment of a regulated facility, etc.

Specified Intermediate outcome – Those intermediate Outcomes specified by the EPA in the RMCEI Return template

TARGET - Once the baseline is established, the goal should be to reduce/increase the baseline value over time, thereby achieving the intermediate outcome. A target is the value to which the baseline value is aimed to be reduced (or increased) to for that year. A qualitative target can be developed where a baseline has not been established or targets may also be set centrally to ensure a consistent approach to achieving an intermediate outcome/objective”

VOC – Volatile Organic Compounds;

WEEE – Waste Electrical & Electronic Equipment;

WERLA – Waste Enforcement Regional Lead Authority;

WFD – Water Framework Directive;

WFP – Waste Facility Permit.

# Introduction

## Plan Details

Table 1: Plan Details

| Geographic Area | 6,149 square kilometres |
| --- | --- |
| Population | 192,995 (based on census 2022) |
| Calendar Year | 2026 |
| RMCEI Coordinator Name and Position | TH, Assistant Scientist FD, Assistant Scientist |

## Expected Known Once-Off Challenges that may be Faced in Implementation of this Plan

Table 2 Expected Known Once-Off Challenges that may be Faced in Implementation of this Plan (if any) & how these will be Addressed

Description of known challenge and outline of how these will be addressed

1. We are awaiting to backfill 3 positions and these will be allocated throughout the sectors. Interviews will be held in March 2026

2.

3.

4.

5.

## Staff Structure

The organogram below illustrates the organisational structure in the Environment Section (excluding Kilconnell Landfill and Climate Change). The detailed staff requirement for completion of the plan is set out in Section 4. This includes time for both planned and unplanned inspections and includes time allocated for preparation of plans and monitoring programmes, inputting of results, update of databases, follow up action, correspondence, reporting etc.

Figure 1 Council Organogram

| Ref. No | National Environmental Priorities | Have the relevant NEP activities for focus been incorporated into your inspection plan for the year ahead? |  | Where you have answered ‘No’ please provide a comment to explain. |
| --- | --- | --- | --- | --- |
|  |  | Yes | No |  |
| 1.0 | Water - Improving Water Status in all waterbodies |  |  |  |
| 1.1 | Pressures from Agriculture (Farmyards) - slurry/soiled water collection and storage | Y |  |  |
| 1.2 | Pressures from Agriculture (Farmland) - slurry and fertiliser spreading | Y |  |  |
| 1.3 | Discharge Licences/ Misconnections | Y |  |  |
| 1.4 | Local Water Quality Pressures including Septic Tanks and Private Water Supplies | Y |  |  |
| 2.0 | Air - Protecting public health and to improve and maintain air quality |  |  |  |
| 2.1 | Solid Fuel | Y |  |  |
| 2.2 | Air Quality Monitoring and Data Use | Y |  |  |
| 2.3 | Environmental Noise Directive (END) Activities | Y |  |  |
| 2.4 | Local Air and Noise Investigations | Y |  |  |
| 3.0 | Waste - Improving waste management and protecting our environment |  |  |  |
| 3.1 | Tackling illegal waste activities and Multi-Agency Sites/Operators of Concern | Y |  |  |
| 3.2 | Construction and Demolition Material | Y |  |  |
| 3.3 | Household Waste | Y |  |  |
| 3.4 | Commercial Waste | Y |  |  |
| 3.5 | Plastics and Producer Responsibility Initiatives | Y |  |  |

# Priorities for Environmental Enforcement for the Year Ahead

## National Environmental Enforcement Priorities for the Year Ahead

Table 3 National Environmental Priorities Che

## Ongoing RMCEI/Local Priorities

Table 4  Additional Local Priorities

| Local Priorities | Yes | No | Where you have answered ‘Yes’ please provide a summary of the local priorities for the year ahead |
| --- | --- | --- | --- |
| Are there additional local priorities for the year ahead which are not activities for focus under the NEPs? | Yes |  | Please see local priorities outlined at the end of Appendix 1 |

Table 5  Work Planned with Regional Lead Authorities

| Authority | Plans for the Year ahead |
| --- | --- |
| This may include work with some of the following bodies not referred to above: e.g. WERLA, Teagasc & Dept of Agriculture Food & the Marine (DAFM), EPA, DCEE, DHLGH, LAWPRO If all such work has already been referred to above leave this blank. | All collaboration work is included in the National Enforcement Priorities in Appendix 1 |

# Risk Assessment

The regulated installations, including Section 4 Discharge Licences, Waste Permit Facilities and Certificate of Registration sites and Waste Collection Permit operators have been assessed in order of risk and resources are allocated accordingly. The Waste Permit Facilities and Certificate of Registration sites risk register was updated for 2026 and the Discharge Licences risk register is updated on an ongoing basis as results are received. The excel files are too large to add to this plan, however, a copy of the risk registers can be made available to the EPA on request.

At present, GCC have not been provided with any direction to undertake inspections of specific sites by lead authorities.

Table 6 Selection of Sites for Assessment in the Year Ahead

| Type of Regulated Installation (i.e. Discharge Licences/ Waste Permit Facilities / Certificate of Registration / Sites licensed under the Air Pollution Act / etc) | Total No. of Installations in your functional area | Total No. of Installations in your functional area Per Risk Category |  |  | No. Of Inspections Planned Per Risk Category |  |  | Total No. Of Inspections Planned | Additional Comment (e.g. include rationale for selection of sites to be inspected and/or indicate whether any of the inspections planned include installations that have been recommended for inspected by Lead Authorities) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | A | B | C | A | B | C |  |  |
| Discharge Licences | 144 | 7 | 35 | 102 | 1 | 1 | 1 | 144 | Each site is inspected once per year as part of the planned monitoring programme. Enforcement action in terms of warning letters, notices, follow up inspections etc is concentrated on high-risk sites. Resources are not available to plan more than one inspection per site. |
| Waste Permit Facilities | 21 | 5 | 12 | 4 | 1 | 1 | 1 | 21 | Each site is inspected once per year as part of the planned monitoring programme. Enforcement action in terms of warning letters, notices, follow up inspections etc is concentrated on high-risk sites. Resources are not available to plan more than one inspection per site. |
| Certificate of Registration | 3 | 0 | 0 | 3 | N/a | N/a | 1 | 3 | Each site is inspected once per year as part of the planned monitoring programme and enforcement will be carried out if necessary. |
| Sites licensed under the Air Pollution Act | 4 | 0 | 0 | 4 | N/a | N/a | 1 | 4 | Each site is inspected once per year as part of the planned monitoring programme and enforcement will be carried out if necessary. |
| Sewage sludge registered facilities | 3 | 0 | 0 | 3 | N/a | N/a | 1 | 3 | Each site is inspected once per year as part of the planned monitoring programme and enforcement will be carried out if necessary. |
| Total No. Of Inspections Planned |  |  |  |  |  |  |  | 364 |  |

# Resource Assessment for the Year Ahead

## Review of the Achievement of the Previous Years Inspection Targets

Table 7 Review of Previous Years Inspections

| Inspection Type Figures available from your RMCEI return (Section 6) or previous years RMCEI plan | No. of Planned Inspections set out at the start of the Previous Year | No. of Completed Inspections at the end of the Previous Year | Outline any reason for significant difference in completed versus planned figures (i.e. +/- 25%) | Please provide a brief narrative to demonstrate that the previous years completed inspections have been considered when planning the inspections for the year ahead |
| --- | --- | --- | --- | --- |
| Routine Waste Inspections | 394 | 466 |  | Planned inspections are in line with previous years |
| Non-Routine Waste Inspections | 742 | 1149 | A review of how the community wardens record their inspections was carried out in 2025 and this lead to an increase in the number of inspections recorded | This number will be increased in the 2026 plan |
| Routine Litter Patrols/Investigations | 845 | 835 |  | Planned inspections are in line with previous years |
| Routine Water/Wastewater Inspections | 1845 | 1771.5 | A larger number of routine farm inspections were carried out than planned | The number of planned routine farm inspections will be increased for 2026 |
| Non-Routine Water/Wastewater Inspections | 60 | 106 | A larger number of complaints were received than anticipated in relation to water pollution in general and on farms | This number will be increased in the 2026 plan |
| Routine Air/Noise Inspections | 42 | 61 | There was a focus on carrying out inspections on solid fuels in 2025 | This was considered when planning for 2026 |
| Non-Routine Air/Noise Inspections | 2 | 14 | A larger number of complaints were received than anticipated | This number will be increased in the 2026 plan |
| Routine producer Responsibility Inspections | 86 | 89 |  | Planned inspections are in line with previous years |
| Planning inspections | 234 | 328 | Larger number of referrals from the planning department were received than anticipated | A larger number of inspections will be planned for 2026 based on the 2025 number |

## Number of Staff Days Available

Table 8 Resources Available to undertake required Work for the Year Ahead

| Department | Available Resources | Role | Focus Area for this Resource (please ensure you outline which NEP area this resource will be associated with) | Available days for RMCEI (both routine and non-routine) | Basis of calculating Resource Available days (take account of e.g. job-sharing, full/part-time working, expected leave, secondment to other work areas and therefore unavailable, basis for a standard working year e.g. 220 days) |
| --- | --- | --- | --- | --- | --- |
| Environment Section | AD | Senior Executive Scientist | Management – Waste, Water, Air, Noise, Planning Health & Safety | Management |  |
| Environment Section | HR | Executive Scientist | RMCEI Management Discharge Licences Sampling Water Complaints Planning | 210 |  |
| Environment Section | TH | Assistant Scientist | RMCEI management Waste Enforcement Waste Permits & Certs Planning PRI’s Collectors and Returns H&S | 168 | One day per week work share |
| Environment Section | BG | Assistant Scientist | Waste management ADI Initiative Waste Enforcement Section 34C Register Article 27, Article 28 Collectors and Returns Oil pollution Planning | 210 |  |
| Environment Section | CK | Assistant Scientist | NAIP All related Agricultural activities Complaint investigation National working Group NAIP Delivering presentations | 210 |  |
| Environment Section | FD | Assistant Scientist | RMCEI management Planning Discharge Licences Catchment Management Bathing Water National Inspection Plan Water Complaints | 210 |  |
| Environment Section | DOC | Assistant Scientist | Waste Enforcement ELVs and Tyres PRIs Illegal waste collectors Planning Waste / Air Complaints Air Planning Farm Inspections | 210 |  |
| Environment Section | CC | Executive Technician | Sampling Bathing Water Planning National Inspection Plan Farm inspections | 210 |  |
| Environment Section | BOS | Environmental Technician Grade 1 | National Inspection Plan Oil Pollution Planning Air Farm inspections Water / Air Complaints | 210 |  |
| Environment Section | BML | Environmental Technician Grade 1 | Solid Fuel Waste Enforcement Air / Noise Collectors and Returns Planning | 210 |  |
| Corporate Services | 15 Community Wardens | Community Wardens | Complaint Investigation | 315 Approx | 15 CW (10% of time assigned to Environment but this will be reviewed in line with community warden review during 2026) |
| Environment Section | HH | Assistant Staff Officer | RMCEI | 210 |  |
| C & E Fire Service Housing Section Water Services | Various | Small area of work related to RMCEI as per detailed plan | Tidy Towns Fire Certificates Housing Inspections GWS Management | N/a | Small area of work related to RMCEI as per detailed plan |
| TOTAL DAYS AVAILABLE |  |  |  | 2373 | Based on 220 days available per person with 10 days reduction for CPD / Training |

## Environmental Enforcement Training Requirements

| Course/Training provided to enforcement staff in previous year: | Course/Training provided by: | Comment |
| --- | --- | --- |
| IMO OPRC -HNS introduction level | Gorton Response Limited | Hazardous chemical spill training |
| Planning and Environment | Southern Regional Waste Management Office |  |
| National Agricultural Inspection Programme training | EPA and LASNTG |  |
| Excel intermediate/advanced | Galway County Council |  |
| Circular economy & resource Waste Management Plans | LEAP |  |
| Training on how to interpret Ambient Air Quality | EPA |  |
| Repak -Compliance Matters: Strengthening Oversight of Suspected Major Producers, Collaboration | Repak |  |
| Waste collection permit training | NWCPO |  |
| LA Air quality network | LAIN Group |  |
| EPA Air Event | EPA |  |
| Public Sector Equality and Human Rights training | Values Lab |  |
| Security Awareness Training | KnowBe4 |  |
| Cyber Security Training | Galway County Council |  |
| Data Breach Procedures Training | Galway County Council |  |
| GDPR Awareness Training | Galway County Council |  |
| Bathing water workshop | EPA |  |

| Course/Training planned for enforcement staff for the reporting year: | Course/Training provided by | Comment |
| --- | --- | --- |
| Drone training | Galway County Council |  |
| Regulation of waste activities | WERLA and ATU |  |
| Site Suitability Assessment for On Site Wastewater Treatment Systems | LASNTG |  |
| Odour impact assessment training | EPA |  |
| Waste case studies conference | EPA |  |

| Training is linked to PMDS Personal Development Plans |  |
| --- | --- |
| Yes/No | If answered No, state your reasoning. |
| Yes |  |

## Health and Safety

Planned Health and Safety training for the reporting year:

- Toolbox talks - Staff members received training on fire and evacuation, fire extinguishers and training to be a fire warden - Staff members whose certification was out of date, completed the Safe Pass course - Staff members attended the annual 1-day H&S seminar ran by Galway County Council. This included talks on gas line safety, pre-work checks and personal safety in the workplace - Refresher training on lone working app

Comments: Galway County Council have obtained OHSAS 18001 certification for Health and Safety. To retain this certification considerable staff resources are required. All persons undertaking site inspections shall ensure adherence to the following: - All employees shall comply with Galway County Councils Health & Safety policies, plans and programmes. - All Inspectors shall carry their Identification Cards and their Certificates of Authorisation with them. - All Inspectors shall ensure that they have all the necessary PPE prior to any site inspection. - Inspectors shall make themselves known to company personnel (where applicable) and adhere to company health and safety policies and wear any personal protective equipment provided. - Where an Inspector feels threatened or obstructed during the course of his or her duties, consideration shall be given to leaving the site and requesting the assistance of the Garda Siochána.

# Planned Inspections/Other Activities for the Year Ahead

## Planned Routine & Non-Routine Inspections

Please see Appendix 1 which is included with this submission

## Outstanding Enforcement Actions & Complaints Requiring Resources for the Year Ahead

Table 9 Outstanding Enforcement Actions & Complaints to be Closed Out

| Inspection Type | No. of Inspections to close out in the Year Ahead | Estimate time per inspection+ write up (days) | Time for all Inspections (days) |
| --- | --- | --- | --- |
| Outstanding Complaints |  |  |  |
| 4.1.1 Litter (excluding fly tipping and illegal dumping) | 22 | 1 | 22 |
| 4.1.2 Waste, non C&D. Includes fly tipping and illegal dumping | 533 | 1 | 533 |
| 4.1.3 Waste, C&D. | 23 | 1 | 23 |
| 4.2 Water/Wastewater | 48 | 0.3 | 13 |
| 4.3 Air/Odour | 11 | 0.2 | 2 |
| 4.4 Noise | 6 | 0.2 | 1 |
| Outstanding enforcement Actions |  |  |  |
| Warning Letters | Not available from current IT systems |  | 10 |
| Section Notices | Not available from current IT systems |  | 10 |
| Complaints | As above |  |  |
| Court Cases | 27 cases open | 1 | 27 |
| Other |  |  |  |
| Total | 670 |  | 641 |

## Summary of Resource Requirements

Table 10 Summary of Inspections to Complete and Resources Required for the Year Ahead

| Inspection Type | No. of Inspections Planned for the Year Ahead | Total Time for all Inspections (days) |
| --- | --- | --- |
| Total Routine Inspections (obtained from Appendix 1: Planned Routine & Non-Routine Inspections for the Year Ahead) | 3580 | 1192.5 |
| Total Non-Routine Inspections (obtained from Appendix 1: Planned Routine & Non-Routine Inspections for the Year Ahead) | 1068 | 637 |
| Outstanding Enforcement Action & Complaints to be Closed out – (outlined in Table 9) | 670 | 641 |
| Additional work priorities for GCC | 0 | 445 |
| Totals | 5318 | 2915.5 |
| Total Available Resources (Days) – (outlined in Table 8 of the Plan) |  | 2373 |

There is a shortfall of five hundred and forty two point five (542.5) days between the available resources and the total days needed to carry out the work plan. This will be overcome by the appointment of three new staff members during the year.

# Plan Review Mechanisms

Table 11 Summary checklist of plan review mechanism

| Question | Yes | No |
| --- | --- | --- |
| Q1 Have progress implementation meetings been planned to be undertaken to assess Plan progress through the year? | Yes |  |
| Q2 Will the Director of Services, Senior Management and Environment Strategic Policy Committee be informed of Plan progress (on a monthly or quarterly basis). | Yes |  |
| Q3 Are objectives for the delivery of the RMCEI Plan incorporated within staff PMDS Team Development Plans? | Yes |  |
| Q4 If aspects of the Plan need to change (i.e. achieved good progress in some areas and are behind in other areas), as a result of a quarterly review, is there a mechanism in place to implement the change? | Yes |  |
| Q5 Will monitoring of the progress of the Plan be documented (i.e. monthly/quarterly monitoring reports, preparation of minutes and circulation of same in relation to any progress meetings)? | Yes |  |
| Q6 Were these plan review mechanisms implemented in the previous reporting year? | Yes |  |

| Q7 What frequency will the plan progress be reviewed? | Monthly |
| --- | --- |

# Use of Relevant Inspection Templates

Table 12 Summary of waste inspection template use for the reporting year

| Has the use of relevant waste inspection templates been incorporated into your enforcement work for the year ahead? (Yes/No/Not for all applicable work areas) | Where you have answered ‘No’ or ‘Not for all applicable work areas’ then please provide a comment, with reference to the relevant template(s) not being used. |
| --- | --- |
| Yes |  |

- Appendix 1: Planned Routine & Non-Routine Inspections for the Year Ahead

To be populated in the Excel Spreadsheet RMCEI Plan Appendix 1-Planned Routine & Non-Routine Inspections for the Year Ahead. Available on the NIECE Portal and to be submitted with the RMCEI Plan.

Unless directed otherwise

Relevant waste inspection templates are available on the WERLA page of the NIECE Portal.